U.S. Department of State

Bureau of International Narcotics and Law Enforcement Affairs (INL)

[INSERT PROJECT NAME HERE]

Monitoring and Evaluation Plan

FY19-FYXX

Drafted by:  [INSERT POC AT PARTNER]

Approved by: [INSERT INL PROGRAM OFFICER and M&E OFFICER]

Title:

[PROJECT NAME] POC:

Date:  XX

ACRONYMYS

| DOS | (United States) Department of State |
| --- | --- |
| FBS | Functional Bureau Strategy |
| INL | Bureau for International Narcotics and Law Enforcement Affairs |
| M&E | Monitoring and evaluation |
| PIRS | Performance Indicator Reference Sheet |
| PITT | Performance Indicator Tracking Table |
| PrMEP | Project Monitoring and Evaluation Plan |

TABLE OF CONTENTS

Contents

1.	INTRODUCTION	4

1.1	Program Summary	4

1.2	M&E Roles and Responsibilities	5

2.	THEORY OF CHANGE	6

2.1	Theory of Change Statement	6

2.2	Results Framework	7

2.3	Logic Model	7

3.	PERFORMANCE MONITORING AND REPORTING	10

3.1	Results and Performance Indicators	10

3.2	Indicator Baselines and Targets	11

3.3	Indicator Data Collection Tools and Methodologies	11

3.4	Indicator and Data Reporting	12

4.	DATA MANAGEMENT	12

4.1	Data Collection	12

4.2	Data Quality	12

4.3	Data Storage	13

4.4	Data Security	13

4.5	Data Analysis and Use	13

5.	EVALUATIONS, ASSESSMENTS, STUDIES, AND OTHER ANALYSES	13

Annex A:  Performance Indicator Tracking Table	14

Annex B:  Performance Indicator Reference Sheets (PIRS)	15

# INTRODUCTION

This Project Monitoring and Evaluation Plan (PrMEP) will be used by _______________ (partner) and INL to monitor and track the results of the __________________ project.  Through this PrMEP, _______________ (partner) has ensured alignment of sub-objectives and indicators with the INL Functional Bureau Strategy (FBS), and will remain flexible to incorporate new indicators and data collection and evaluation methodologies as the program may evolve. Throughout implementation of the project, _______________ (partner) will ensure that rigorous monitoring methods will be used, along with data collection instruments and sampling frameworks that will provide high-quality baseline and performance data to allow before-and-after comparisons of key performance indicators.

This PrMEP uses guidance from several US Department of State and USG regulations, strategies, and official guidance documents, such as:

- 18 FAM 301.4, Department of State Program and Project Design, Monitoring, Evaluation, and Evaluation

- INL Bureau Strategic Framework

- Program Design and Performance Management Toolkit (and all related individuals templates and guidance documents)

- State-USAID Joint Strategic Plan;

- President’s Initiative to Stop Opioid Abuse and Reduce Drug Supply and Demand and Integrated Strategic Framework to Reduce Illicit Drug Availability in the United States;

- Executive Order 13773: Enforcing Federal Law with Respect to Transnational Criminal Organizations and Preventing International Trafficking;

- National Drug Control Strategy; and

The PrMEP is a living document.  When relatively substantial changes are made in M&E planning and programming, this PrMEP will be modified by _______________ (partner) and then submitted to INL for review and approval.  It is recommended that the PrMEP be reviewed on an annual basis.

## Project Summary

## M&E Roles and Responsibilities

M&E technical direction for this project will be provided by _________________, under the direction of __________________.  Mr./Ms. ___________ will be responsible for coordinating and managing all data collection, M&E-related evaluations and assessments, and other M&E-related tasks.  Additionally, while several _______________ (partner) staff, government counterparts, and other stakeholders are involved in some manner in monitoring and evaluating the progress of this project, there are particular staff members from _______________ (partner) who are responsible for implementing this PrMEP, as summarized below in Table 1.  Table 1 is illustrative of the roles and responsibilities of personnel, and is not exhaustive.

Table 1: Project M&E Roles and Responsibilities

| Personnel Title/Position | Specific M&E Plan Roles and Responsibilities |
| --- | --- |

# THEORY OF CHANGE

## Theory of Change Statement

As mentioned above, the project’s overarching goal is ________________.  The theory of change statement for the project is:

IF ________________; and

IF ________________________;

THEN _______________.

## Results Framework

A Results Framework (RF)is a structured approach to project design and performance measurement that is based on well-defined results and a coherent, streamlined strategy to achieve those results. The RF for the project, presented in Figure 1 below, conveys the project’s theory of change, linking the necessary and sufficient results of the project to the overall FBS strategy and other related Program Goals and Objectives, and accompanying threats and assumptions.  The RF provides a guide to help _______________ (partner) and INL management and staff accomplish intended results and provides lists of risks and assumptions that could affect various outcomes. ____________ (project) has ______ Objectives against which it will be measuring progress and is the project’s theory of change.

Figure 1: Project Results Framework

## [INSERT RESULTS FRAMEWORK

## Logic Model

# PERFORMANCE MONITORING AND REPORTING

_______________ (partner) will periodically assess underlying critical assumptions and causal linkages within the RF and Logic Model to guide implementation, adapt to changes, and scale up successful interventions based on evidence. As a part of this approach, _______________ (partner) will undertake rigorous monitoring of the Program. However, performance monitoring goes beyond just indicator data collection and monitoring.  This section illustrates how _______________ (partner) will effectively monitor activity performance; utilize effective data collection and analysis resources; and establish systems that ensure that the data being collected is of high quality and are important components of a useful performance monitoring system.

## Results and Performance Indicators

The PrMEP includes indicators that we propose are necessary for _______________ (partner) to track the Project’s performance.  These indicators are sufficient to enable a full report on the achievement of each intended objective. It does not include internal indicators that _______________ (partner) may utilize for general management; balancing the reality of the associated expense of collecting and reporting on related data and using indicators that are most necessary to give an accurate measure of the attainment of the results. Table 2 presents the Project’s indicators for its Goal and Objective levels.  These indicators are a balanced mix of USG “Standard” (“F”) Indicators; FBS Indicators, and Custom Indicators.  The F and FBS Indicators are marked in parentheses.

_______________ (partner) has incorporated as many F-Indicators as possible for its performance monitoring indicators. Where applicable, indicators will be disaggregated by sex and by any other appropriate categories, such as region, country, or type-of-beneficiary. etc. Specific indicator disaggregation requirements are provided in the PIRS for each indicator. The _______________ (partner) M&E Specialist will be ultimately responsible for reporting on all of the Program’s performance indicators.  _______________ (partner) staff will work with appropriate entities to load all relevant indicators and data information into any and all relevant _______________ (partner or project) data collection systems, including, but not limited to, performance results, geospatial coordinates, success stories, and photographs.

Annex ____ presents the project’s Performance Indicator Tracking Table (PITT), a comprehensive table (in Excel format) of project’s indicators, indicating which indicators are Standard/F, FBS, and Custom Indicators and the indicators’ definition/description, data source and collection method(s), baseline information, and targets throughout the life of the project.  This PITT can record and present additional information (such as quarterly and/or annual performance data), if necessary, and can be customized for the various types of reporting needs _______________ (partner) staff may have.

Table 2:  Objective 1.1. Program Indicators

| Sahel Road Safety Initiative Project Goal: |  |  |  |
| --- | --- | --- | --- |
| High-level Goal Indicators: • G-1: • G-2: |  |  |  |
| Objective 1: | Objective 2: | Objective 3: | Objective 4: |
| Objective 1 Indicators: 1.1 - 1.2 - 1.3 - 1.4 - | Objective 2 Indicators: 2.1 - 2.2 - 2.3 - 2.4 - | Objective 3 Indicators: 3.1 - 3.2 - 3.3 - 3.4 - | Objective 4 Indicators: 4.1 - 4.2 - 4.3 - 4.4 - |

## Indicator Baselines and Targets

18 FAM 301.4-3 requires that a methodology for collecting baseline value be established, which should be collected before or at the state of a program or project, and should be utilized to establish targets.

Targets will be refined as more information becomes available. The PITT at Annex ___ will provide the baselines and targets for all project indicators from FY19 to FY22, with the baseline collection date and current baseline value.  At the time of this PrMEP submission (January ____, 2020), many of the baselines and targets are TBD because the Indicator Baseline Data Collection that will establish the baselines and targets has not yet been conducted.

## Indicator Data Collection Tools and Methodologies

_______________ (partner) staff will collect and analyze project data on a regular basis across its programming, in order to monitor the progress and performance.  _______________ (partner) staff will systematically track the goal-level and Objective-level indicators outlined in project’s Logical Framework.  _______________ (partner) will also use ____ cross-cutting indicators that will specifically measure __________________.

_______________ (partner) staff will work with INL to utilize any current and existing DoS and INL indicators, systems, and tools.  Below is an illustrative list of data collection tools and methodologies, which will be updated periodically by _______________ (partner) staff.

- Perception Surveys:  Some programs may conduct in-person perceptions surveys to collect baseline and ongoing performance data.

- Geographic Information Systems (GIS): _______________ (partner) will work towards collecting data that will be geo-referenced in view of mapping, quality assurance and spatial analysis, where appropriate.

## Indicator and Data Reporting

Reporting is due on a quarterly and annual basis.  _______________ (partner) will submit all indicator data through its PITT, which will be Excel-based, and as an annex to its quarterly and annual reports, which are sent directly to INL program staff for review.  In addition to a careful review of the data, INL program officers may coordinate with counterparts at Post to conduct data validation exercises, including site visits, any third-party monitoring, and document reviews, to ensure that _______________ (partner)’s reporting is accurate and credible.

# DATA MANAGEMENT

## Data Collection

## Data Quality

In order to ensure that data is high quality, _______________ (partner) will conduct data quality assessments (DQAs) on the DoS’s five data quality standards (validity, integrity, precision, reliability and timeliness) for data reported on all standard indicators, certain custom indicators, and any other indicators reported to Washington (in accordance with 18 FAM _______).  These DQAs will be conducted, at a minimum, every three years for each Washington-reported indicator. The DQA findings should be documented in the PIRS for each indicator and not whether any mitigating actions are being taken to improve data quality.  These DQAs will be coordinated by the INL M&E Specialist and could be conducted by INL staff and/or external consulting individuals or contractors.  He/she will also lead all internal INL data quality mechanisms and DQAs.  Those conducting DQAs will use the Data Quality Assessment Tool for each indicator DQA.

_______________ (partner) will establish quality control mechanisms to ensure that quality data is used to monitor the project’s progress and inform activity decision-making. A detailed project data quality assurance guideline will be developed, highlighting day-to-day guidance on data quality, supervision, and regular internal DQAs to be undertaken periodically.  The planned DQA dates are identified on the Performance Indicator Reference Sheets (PIRS).

## Data Storage

## Data Security

## Data Analysis and Use

# EVALUATIONS, ASSESSMENTS, STUDIES, AND OTHER ANALYSES

Evaluation is the periodic assessment of an activity’s relevance, performance, and efficiency in relation to stated objectives. Table 3 below summarizes the various evaluations, assessment, studies, or other analyses that _______________ (partner) staff and/or external contractors may undertake in relation to the project’s monitoring and evaluation tasks and activities.  These tasks could range from planned performance or impact evaluations, to baseline data collection activities and programming assessments.

Table 3:  Evaluations, Assessments, Studies, or Other Analyses Related to the Project’s Monitoring and Evaluation Tasks

| Name of Evaluation, Assessment, or Study | Estimated Date of Implementation (to Completion) | Main Office Responsible | Additional Partner Involvement |
| --- | --- | --- | --- |
| EXAMPLE: Project Indicator Baseline Data Collection |  |  |  |
| EXAMPLE: Baseline, midline and perception Surveys |  |  |  |
| EXAMPLE: Cost-Benefit Analysis |  |  |  |

##### Annex A:  Performance Indicator Tracking Table

##### Annex B:  Performance Indicator Reference Sheets (PIRS)