# Sample State Agency and Implementation Activities/Indicators Tracker Table

Objective: improve access to local foods in eligible CNP sites through comprehensive farm to school programming that includes local sourcing and agricultural education efforts.

| Activity (Repeat table headings if table extends to multiple pages) | Activity Category | Indicator(s) | Anticipated Start Date (Month, Year) | Anticipated Completion Date (Month, Year) | Responsible Party (Name, Title, Organization) |
| --- | --- | --- | --- | --- | --- |
| Attend at least one national or regional-level networking and training event. | Required (this is the only required activity. Do not enter this for any other row) | Number attended | Sept. 2025 | Sept. 2025 | Project Manager |
| Example: Recruit and convene a local foods student/staff advisory committee | Enter “Local Sourcing,” “Agricultural Education,” or “Both.” Example: Local Sourcing | Example: Number of primary students (grades k-5) impacted Number staff attended | Example: Oct. 2025 | Example: June 2026 | Example: Jessica Plum, Registered Dietitian, Food and Nutrition Service Department |
| Example: Deliver training to five farm to school teams, representing multiple States, in a regional farm to school institute. | Enter “Local Sourcing,” “Agricultural Education,” or “Both.” Example: Local Sourcing | Example: Number staff Trained Dollar amount of local foods purchased by product type: fruit, vegetables, fluid milk, other dairy, protein, grains (including baked goods), other (please specify) | Example: June 2026 | Example: July 2026 | Example: Sam Cooke, Director, Example Nonprofit, Inc. |
| Example: Convene an education and school garden committee that identifies areas for potential curriculum integration, project goals, roles and responsibilities, timeline, budget, and funding strategy | Enter “Local Sourcing,” “Agricultural Education,” or “Both.” Example: Agricultural Education | Example: Number of secondary students (grades 6-12) impacted Number staff attended | Example: Sept. 2025 | Example: June 2026 | Example: Ms. Green, Elementary Science Coordinator, ABC School District |
| Example: Install ten raised beds to expand school garden | Enter “Local Sourcing,” “Agricultural Education,” or “Both.” Example: Agricultural Education | Example: Number of gardens completed | Example: March 2026 | Example: April 2026 | Example: Mr. Williams, Head Custodian, ABC Elementary |