## Milestone Schedule
Milestone # | Milestone | Exit Citeria/Deliverable | Due Date | Payment | Funded | CLIN SUBCLIN | ACRN
1 | Project Kickoff meeting and collaborative program review of intervention strategies and technology; all supporting positions identified in the proposal are assigned to personnel and names are provided to DARPA; all personnel working on the Program must be identified | Progress Report | Month 1
2 | Report on proposed mechanisms, metrics, and relationship to psychological resilience and operational readiness outcomes; all proposed personnel must be working on the effort at the planned level of effort; preregistration of intervention studies | Progress Report; Preregistration number(s) | Month 2
3 | Submission (as necessary) of Independent Review Board (IRB)-approved protocol(s) for Human Subjects Research for secondary Human Research Protection Office (HRPO) review | IRB-approved protocol(s) | Month 3
4 | Sleep intervention system prototype (hardware and software) preliminary demonstration | In-person demonstration of working technology; Progress Report | Month 6
5 | Begin human subjects research activities for Intervention | Progress Report | Month 9
6 | Preliminary assessment of intervention effects on macro- and micro-architectures and on cognitive performance measures | Progress Report, including review of preliminary data and code | Month 12 |  | 0 | TBD | TBD
7 | Submission of IRB-approved amendments of any necessary intervention changes for secondary HRPO review | IRB-approved protocol(s) with amendments | Month 15 |  | 0 | TBD | TBD
8 | Report on refined intervention and resilience & operational readiness assessment strategy for notional 12-month expansion | Draft statement of work (SOW) and rough order of magnitude (ROM) cost for potential 12-month expansion. | Month 18 |  | 0 | TBD | TBD
9 | Evaluation of program metrics | Evaluation report, including review of data and code | Month 21 |  | 0 | TBD | TBD
10 | Feasibility report on ability to modulate the target mechanism(s), including final model for specifying the relationship between neural stimulation, REM and NREM sleep, target neural mechanisms, and program outcomes | Final Report | Month 24 |  | 0 | TBD | TBD
Total |  |  |  | 0
HIGHLIGHTED SECTION NOT TO BE FILLED OUT BY PROPOSERS